## Sheet1
CDR_PROCESSOR TABLE MISSIONS
mission	estimated time	De-facto time

create use-case diagrams.	4 hours	1 hour
create processor h files – high level design.	8 hours	4 hours
create protocol with feeder h file.	4 hours	1 hour
create processor ADT’s.	12 hours	8 hours
test processor ADT’s.	4 hours	4 hours
create transmission channel with feeder.	8 hours
test transmission channel with feeder.	4 hours
create processor makefile	4 hours	2 hours
implant log in processor.	4 hours	2 hours
adapt the protected hashmap for safe changes of stored data.	4 hours	2 hours
create communication channel module with feeder.	4 hours
test changes in the adapted hashmap and log implantation.	4 hours	2 hours
create new description of HLD and processor LDD	4 hours	1.5 hours
implant log in communication channel.	4 hours	2 hours
create query module in processor	8 hours
test query module in processor	4 hours
implant log in query module	4 hours
create management API and module	4 hours
test management module	4 hours
test CDR processor with multi threads	8 hours